## Risk Register
Risk Exposure Calculator
Score = Likelihood × Impact ¦ Priority: 1–4 Low, 5–9 Medium, 10–16 High, 20–25 Critical
Risk ID | Description | Likelihood (1–5) | Impact (1–5) | Score (L×I) | Priority | Response
R-001 | Key staff member leaves during project | 3 | 4 | 12 | High | Knowledge transfer plan
R-002 | Funding delayed or reduced | 4 | 5 | 20 | Critical | Maintain reserve fund; escalate early
R-003 | Scope creep from stakeholders | 4 | 3 | 12 | High | Change control process
R-004 | Supplier fails to deliver on time | 2 | 4 | 8 | Medium | Identify backup suppliers
R-005 | Data breach or IT failure | 2 | 5 | 10 | High | IT security review; backup policy
R-006 | Low volunteer/staff engagement | 3 | 3 | 9 | Medium | Regular check-ins; recognition
R-007 | Venue cancellation for key event | 1 | 4 | 4 | Low | Contingency venue booked
R-008 | Regulatory/compliance change | 2 | 3 | 6 | Medium | Monitor legal updates quarterly
R-009 | Poor stakeholder communication | 3 | 2 | 6 | Medium | Communication plan in place
R-010 | Budget overrun | 3 | 4 | 12 | High | Monthly budget reviews
Summary
Critical risks | 1
High risks | 4
Medium risks | 4
Low risks | 1